## Slide 1: Automated Online CDM Risk Register
Principal Designers Working Group - 27 Jan 2022
Saskia Lear
27th January 2022

## Slide 2: Agenda
Introduction
Common problems with CDM risk registers
Use of Sharepoint Lists
Use of Power Automate
Demonstration (screenshare)

## Slide 3: Introduction
H&S lead on a new National Highways framework (TA2)
Set things up right from the start
  Consistent
  Lessons learnt
  Suitable for GG104
Plan for improvement

## Slide 4: Common Problems
The register itself
QA systems such as ProjectWise ”hide” information until it is issued
  Teams/disciplines don’t have all the information
Different versions of the register on local drives
  Dependant on when team last accessed the joint register
Different formats for risk assessment
  not consistent with GG104 or with eachother
Compatibility of software
  Different teams/organisation have different software, causing errors

## Slide 5: Common Problems
Use of the register
Mitigations develop as design develops
  Designers may leave it to after the design is complete
  or guess at the mitigation at the start and then not update
Risk Owners are just a name on a spreadsheet
  No guarantee that they are aware and managing the risk
Difficult to review
  The amount of information in the full register is often larger than the screen/paper

## Slide 6: Use of MS Lists app
Basics
Web based app
  Part of Office 365 and is embedded within Sharepoint
  MS Teams all have a linked Sharepoint site
  You don’t need to have Ofice 365 to use an existing List
List settings
  Formatting of columns similar to Excel
  Versioning history
  Automated notification emails & alerts when changes made

## Slide 7: Use of MS Lists app
What that means
Anyone with access to Teams site can use it
You can embed it directly into the site (no need to ”open” the document)
Accessible anywhere with internet (even mobile phone on site)
Everyone has the latest information (Consistent with GG104)
Can link documents to risks (ie shape files, design decision reports, etc)
Risk Owner names are also email addresses (automated emails)
Connects with Power Automate for additional automations

## Slide 8: Lists embedded in Project sharepoint

## Slide 9: Different Views

## Slide 10: Use of Power Automate
Online apps can be connected using Power Automate
  Includes online versions of programmes such as Excel
  Automating standard processes to speed up input and reduce errors
Form for initial hazard identification
  Quick and easy way to add new hazard into the risk register
Create a spreadsheet version of the risk register for issue
  Capture live data into suitable Excel template

## Slide 11: Initial Hazard Identification Form
Making it easier to add new hazards to the risk register

## Slide 12: Create Spreadsheet for Issue
Capture live data

## Slide 13
Saskia.lear@arup.com
Saskia Lear